Qupaca x Acadea: AI Ticket Agent

Quinn's Internal Governance & Execution Plan  |  Confidential

# 1. Your Role

Melo builds. You lead. That means:

- You are the single point of contact with Acadea.

- You own all knowledge curation — every doc, ticket export, training video, best practice that feeds the agent.

- You drive the pitch to Kevin Murphy and get written sign-off.

- You coordinate design partner onboarding with Mark's help.

- You track the project against the timeline and flag risks early.

- You and Melo finalize pricing together and you present it to Acadea.

# 2. Pre-Build Checklist (Complete Before Kevin Pitch)

These are your personal action items before the build can start.

| Action | Deadline | Status |
| --- | --- | --- |
| Pull Zendesk ticket field schema (what fields does Acadea's ticket submission form require?) | Today | 🔴 Open |
| Map top recurring ticket types / issue categories (pull from Zendesk history) | Today–Tomorrow | 🔴 Open |
| Ask Troy (IT) to grant Quinn Zendesk admin access | Today | 🔴 Open |
| Begin exporting historical Zendesk tickets for agent training data | This week | 🔴 Open |
| Share Ticketing Best Practices doc with Melo | Today | 🔴 Open |
| Interview Chuck Campbell to surface Kevin Murphy's likely objections (see Section 4) | Before Wed pitch | 🔴 Open |
| Align with Melo on pricing estimate to present to Kevin | Before Wed pitch | 🔴 Open |
| Confirm Melo has read and understood the Build Brief | Day 1 | 🔴 Open |
| Schedule kickoff call with Melo | ASAP | 🔴 Open |

# 3. Weekly Governance Rhythm

Once the build starts, use this structure to stay on top of the project.

- Daily (async): 1 message to Melo — blockers? progress? anything from Acadea side?

- Melo sends Quinn hours worked each day (for billing accuracy).

- Every other day: Quinn checks in with Mark or Chuck with a brief status update (builds trust, keeps champions warm).

- Design partner week: Daily call with Melo to triage bugs and prioritize fixes.

# 4. Chuck Campbell Interview — Pre-Pitch Kevin Prep

Before you pitch Kevin Murphy, have a 10-15 minute call with Chuck to calibrate. Use these questions:

## Opening

- "I want to make sure my pitch to Kevin lands well. You know him better than I do — can I ask you a few things?"

## On Kevin's Priorities

- What does Kevin care most about right now on the tech side — performance, reliability, security, something else?

- How does Kevin typically feel about external tools or vendors touching Acadea's systems? Is he generally open to it, or protective?

- Has Kevin had any bad experiences with third-party integrations in the past that I should be aware of?

## On Decision-Making Style

- Is Kevin more likely to want to see a demo first, or does he prefer to see a written proposal and think it over?

- What level of technical detail does Kevin want in a pitch — high-level outcomes, or does he want to get into the architecture?

- Is there anything that would be an immediate "no" for Kevin — a dealbreaker I should avoid?

## On Concerns He Might Have

- Do you anticipate Kevin having any concerns about Qupaca owning the hosting and having API access to Zendesk?

- Any concerns about data privacy or security given that customer conversations will flow through our system?

- Is there anything about the Zendesk/Jira setup that Kevin is particularly protective of?

## Closing

- "Is there anything you'd recommend I emphasize, or anything I should avoid bringing up?"

- "Would it help if you introduced me and Melo to Kevin before the pitch call, just to warm it up?"

# 5. Post-Approval: Design Partner Onboarding

Once Kevin approves, Mark will facilitate introductions to Peralta and Chaffey. Your job:

- Brief the design partner contacts on what we're building and why they were selected.

- Set expectations: this is a beta, there will be rough edges, their feedback shapes the product.

- Define a testing window (target: March 27–31) and a feedback channel (Slack? Email? Your call).

- Collect specific feedback: did the agent ask the right questions? Did tickets come through correctly? Was the UX clear?

- Triage feedback with Melo daily and ship fixes fast.

# 6. Knowledge Curation Roadmap

This is ongoing work that only you can do. Here is the priority order:

Phase 1 — Before build (this week):

- Share Ticketing Best Practices doc with Melo for agent system prompt bootstrapping.

- Export a representative sample of historical Zendesk tickets — especially threads with back-and-forth Q&A between dev/support and CSMs/customers.

- Document the top recurring issue types (once you have Zendesk admin access from Troy).

Phase 2 — During build and testing:

- Share product demo recordings and training materials for agent context.

- Review and refine the agent's system prompt based on testing observations.

- Identify knowledge gaps — what does the agent not know that keeps producing bad tickets?

Phase 3 — Post go-live (ongoing):

- Monthly review of ticket quality with Acadea support team.

- Update the best practices markdown file as support team identifies new patterns.

- Track: are CSMs still being called? Is ticket quality improving? Are support Q&A threads getting shorter?

# 7. Pricing Worksheet

Use this to prepare your number before the Kevin pitch:

| Component | Notes |
| --- | --- |
| Melo build hours × $62.50 | Melo tracks hours; estimate 40–60hrs → $2,500–$3,750 |
| Quinn hours (PM + knowledge curation) | Do not give this away free. Estimate 15–25hrs → $937–$1,562 |
| Combined build fee | Total cost basis: ~$3,400–$5,300. Price to Kevin at cost or modest markup. |
| Monthly operational fee | TBD based on actual infra + API costs post-launch. Rough estimate: $200–$500/mo. |
| Relationship discount framing | "We're pricing this at cost because we want to prove ourselves. If it works, we'll talk about what's next." |

Quinn's Internal Plan  |  Qupaca  |  Confidential  |  March 2026